## ALL DIVISIONS
No. | General Project Information Briefing Section | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1 | "Are there" | What is the name of the GC or CM that sent the ITB or RFP? | Some projects will have multiple GC or CM Bidders
2 | "what type" | What is the date the ITP or RFP was sent?
3 |  | What is the name, address and phone number of the person who sent the ITB or RFP?
4 |  | What is the Bid Due Date and Time?
5 |  | What documents are included in the ITB or RFP? | Could be: ITB Letter, As-Built Drawings, Plans, Specifications, Pre-Bid RFI's, Photos, Scope of Work Documents, Equipment Lists, Schedules, Special Instructions, GC Rules & Regulations, Bid Forms, Addendums, Contracts, GeoTec Reports, Asbestos Surveys, Calculations, Environmental Site Assessments, Brand Books (Manuals), Insurance Requirements, Sample COI, Technology Maps, Development Orders, Owner Work Letters, Site Logistics Plan, Parking Plan
6 |  | What is the Bid Delivery Method? | Could be: Public Bid Opening, Private Bid using email or Bid Management platform (ie: Building Connected)
7 |  | If it is a Public Bid Opening, what is the Bid delivery address and time of the bid opening? | The Bid Due date and time may be different than the public read alound date and/or time.
8 |  | What are the bid submission requirements? | Could be: Bid Form, Bond, COI, Qualifications. Sometimes in person or by email or Bid Managment Platform.
9 |  | Is there a PRE-BID Job Walk? Is it Mandatory? What is the Date, Time and Location address.
10 |  | What is the name of the Project?
11 |  | What is the City and State the project is located in?
12 |  | What is the street address and zip code of the project?
13 |  | What is the name of the Owner of the project? | This is not always available in the ITB or RFP documents.
14 |  | What is the name of the Architectural firm for the project?
15 |  | What is the full address of the Architectural firm for the project?
16 |  | What is the name of the Project Architect?
17 |  | What is the full address and phone number for the Project Architect?
18 |  | What documents are required for a complete bid submission? | Could be: Signed Bid Form, Bond, COI, Schedule Information, Company or Team Qualifications, Other?
19 |  | What is the project description as written in the Architectural plans? | This information is also included in "some" ITB's from the GC. There is a place for this to be included in the Building Connected ITB.
20 |  | What is the size of the project measured in square feet of the building?
21 |  | What is the start date of the project?
22 |  | What is the end date of the project?
23 |  | What is the duration of the project in Calendar Days? | This would be a calculated number based on the start date and end date
24 |  | What is the cut-off Date and Time for Pre-Bid RFI's?
25 |  | What is the name of the Construction Management Firm? | If there is one?
26 |  | What is the name, Full Address and Contact information of the CM Contact?
27 |  | What is the Name of the Owners Represenative? | If there is one?
28 |  | What is the Name, Full Address and Contact information of the Owners Representive?
29 |  | What is the Project Delivery Method? | Could be: Design-Bid-Build (DBB), Design-Build (DB), Construction Management at Risk (CMAR), Construction Management Multi-Prime (CCMP), Public-Pribvate Partnership (PPP or 3P), Integrated Project Delivery (IPD)

## MECHANICAL
No. | MECHANICAL | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | Skechers ITB Tyler Texas 0Mini | Skechers ITB Tyler Texas 40 | Skechers ITB Tyler Texas 401 | Skechers ITB Tyler Texas 401 mini
1 |  | What is the name and full address of the Mechanical (MEP) Engineering Firm?
2 |  | What is the name of the Mechanical Engineer?
3 |  | What is the full address of the Mechanical Engineer?
4 |  | What Documents are provided specific to Mechanical / HVAC? | Could be: Plans, As-Built Drawings, Specifications, SOW, Special Instructions, Rules & Regulations, Equipment Lists
5 |  | Where are the Mechanical / HVAC specifications located? | Specification Manual or Plans?
6 |  | What Mechanical Building codes are listed on the drawings? | What Building codes are listed on the drawings?
7 |  | Are there Boilers are listed in the Mechanical drawings? | Boilers: Provide hot water or steam for heating systems.
7 |  | Are there Heat Exchangers listed in the Mechanical drawings? | Heat Exchangers: Used to transfer heating and cooling in an an HVAC Piping system.
8 |  | Are there Heat Pumps are listed in the Mechanical drawings? | Heat Pumps: Efficiently provide heating and cooling by transferring heat from one location to another.
9 |  | Are there Unit Heaters are listed in the Mechanical drawings? | Unit Heaters: Small, self-contained heaters used for spot heating or supplemental heat.
10 |  | Are there Radiant Floor Systems are listed in the Mechanical drawings? | Radiant Floor Heaters: Provide heat through pipes or electric mats under the floor.
11 |  | Are there Chillers are listed in the Mechanical drawings? | Chillers: Large, central units that cool water or air for distribution throughout the building.
12 |  | Are there RTU's listed in the Mechanical drawings? | Rooftop Units (RTUs): Also provide cooling, in addition to heating and ventilation.
13 |  | Are there Air Cooled Condensors are listed in the Mechanical drawings? | Air-Cooled Condensers: Used in conjunction with chillers or other cooling equipment to dissipate heat.
14 |  | Are there Air Evaporative Coolers listed in the Mechanical drawings? | Evaporative Coolers: Use evaporation to cool air, often used in dry climates.
15 |  | Are there Mini Split Units are listed in the Mechanical drawings? | Mini-Split Systems: Small, ductless systems that provide cooling and heating to individual zones.
16 |  | Are there AHU's are listed in the Mechanical drawings? | Air Handling Units (AHUs): Distribute conditioned air throughout the building.
16 |  | Are there MUAHU's are listed in the Mechanical drawings? | Make Up Air Handling Units (AHUs): Used to bring in the required amoount of outside / fresh air to a space.
17 |  | Are there Fans are listed in the Mechanical drawings? | Fans: Provide ventilation and air circulation, often used in conjunction with AHUs.
18 |  | Are there ERV's are listed in the Mechanical drawings? | Energy Recovery Ventilation (ERV) Systems: Recover energy from exhaust air and transfer it to incoming fresh air.
19 |  | Are there Ventilation Fans are listed in the Mechanical drawings? | Ventilation Fans: Small fans used to exhaust air from restrooms, kitchens, and other areas.
20 |  | Are there HRV Systems are listed in the Mechanical drawings? | Heat Recovery Ventilation (HRV) Systems: Recover heat from exhaust air and transfer it to incoming fresh air.
21 |  | Are there Humidifiers are listed in the Mechanical drawings? | Humidifiers: Add moisture to the air to maintain a comfortable humidity level.
22 |  | Are there Diffusers are listed in the Mechanical drawings? | Diffusers: Disperse conditioned air into occupied spaces. Getting the quantities will require a "take-off". The schedule will only list the different types.
23 |  | Are there Louvers and Vents are listed in the Mechanical drawings? | Louvers & Vents: Provide a means for air to enter or exit the building. Getting the quantities will require a "take-off". The schedule will only list the different types.
24 |  | Are there Water Storage Tanks or Towers are listed in the Mechanical drawings? | Water Storage Tanks or Towers: Store water for cooling systems.
25 |  | Are there Cooling Towers are listed in the Mechanical drawings? | Cooling Towers: Dissipate heat from cooling systems.
26 |  | Are there Pumps are listed in the Mechanical drawings? | Pumps: Circulate water or other fluids through HVAC systems.
27 |  | Are there expansion tanks are listed in the Mechanical drawings? | Expansion Tanks: In line tanks that allow for the expansion in a closed loop water system.
28 |  | Are there VAV Boxes are listed in the Mechanical drawings? | VAV Box: A Variable Air Volume unit used to distribute and control forces air hearting and cooling to a space.
29 |  | Are there VRF Units are listed in the Mechanical drawings? | VRF Unit: A Variable Refrigeration Volume unit used to distribute and control forced air heating and cooling to a space.
TEST ITB SCOPE QUESTIONS TO BE QUERIED ON THE ITB DRAWINGS - DEFINED BY PETE MCCALL 3/4/25
1 |  | What Drawings are provided specific to Mechanical / HVAC? (Provide a pdf list showing all the Drawing Numbers and Titles) | Could be: Plans, As-Built Drawings, Specifications, SOW, Special Instructions, Rules & Regulations, Equipment Lists
2 |  | Are there RTU's listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Rooftop Units (RTUs): Also provide cooling, in addition to heating and ventilation.
3 |  | Are there PTAC Units listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | PTAC Units are stand alone Heat and Air units typically installed in hotels or multifamily dwelling units.
4 |  | Are there MUAHU's listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Make Up Air Handling Units (AHUs): Used to bring in the required amoount of outside / fresh air to a space.
5 |  | Are there Mini Split Units listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Mini-Split Systems: Small, ductless systems that provide cooling and heating to individual zones.
6 |  | Are there Fans listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Fans: Provide ventilation and air circulation, often used in conjunction with AHUs.
7 |  | Are there Ventilation Fans listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Ventilation Fans: Small fans used to exhaust air from restrooms, kitchens, and other areas.
8 |  | Are there Cabinet Unit Heaters listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Unit Heaters: Small, self-contained heaters used for spot heating or supplemental heat.
9 |  | Are there VAV Boxes listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | VAV Box: A Variable Air Volume unit used to distribute and control forces air hearting and cooling to a space.
10 |  | Are there VRF Units listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | VRF Unit: A Variable Refrigeration Volume unit used to distribute and control forced air heating and cooling to a space.
11 |  | Are there Chillers listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Chillers: Large, central units that cool water or air for distribution throughout the building.
12 |  | Are there Boilers listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Boilers: Provide hot water or steam for heating systems.
13 |  | Are there Cooling Towers listed in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Cooling Towers: Dissipate heat from cooling systems.
14 |  | Are there Pumps isted in the Mechanical drawings? (IF YES - Provide Drawing Numbers and Title) | Pumps: Circulate water or other fluids through HVAC systems.
| NOTE: | If the answer is "NULL" or "NO" answer the question accordingly.

## PLUMBING
No. | PLUMBING | Commercial & Healthcare Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | Skechers ITB Tyler Texas 0Mini | Skechers ITB Tyler Texas 40 | Skechers ITB Tyler Texas 401 | Skechers ITB Tyler Texas 401 mini
1 |  | What is the Name of the Plumbing (MEP) Engineering Firm?
2 |  | What is the name of the Plumbing Engineer?
3 |  | What is the full address of the Plumbing Engineer?
4 |  | What Documents are provided specific to Plumbing? | Could be: Plans, As-Built Drawings, Specifications, SOW, Special Instructions, Rules & Regulations, Equipment Lists, Fixture Schedules,
5 |  | Where are the Plumbing specifications located? | Specification Manual or Plans
6 |  | What Plumbing codes are listed on the drawings?
7 |  | Toilets | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
8 |  | Urinals | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
9 |  | Surgical scrub sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
10 |  | Patient care sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
11 |  | Hand sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
12 |  | Laboratory sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
13 |  | Utility sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
14 |  | Decontamination sinks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
15 |  | Drinking fountains | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
16 |  | Shower fixtures | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
17 |  | Bedpan washers | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
18 |  | Dialysis stations | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
19 |  | Emergency eyewash stations | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
20 |  | Safety shower stations | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
21 |  | Water Systems and Heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
22 |  | Reverse osmosis water systems | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
23 |  | Deionized water systems | These may be listed with the Plumbing Equipment on the drawings. But a reference in the specifications will be where the details will be.
24 |  | Sterile water production equipment | These may be listed with the Plumbing Equipment on the drawings. But a reference in the specifications will be where the details will be.
25 |  | Water purification systems | These may be listed with the Plumbing Equipment on the drawings. But a reference in the specifications will be where the details will be.
26 |  | Large commercial water heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
27 |  | Tank-style water heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
28 |  | Tankless water heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
29 |  | Point-of-use water heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
30 |  | Instantaneous water heaters | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
31 |  | Water Softening equipment | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
32 |  | Pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
33 |  | Booster pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
34 |  | Sewage ejector pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
35 |  | Water Circulating pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
36 |  | Water pressure maintenance pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
37 |  | Medical waste pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
38 |  | Hot water recirculation pumps | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
39 |  | Thermostatic mixing valves | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
40 |  | Emergency shut-off valves | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
41 |  | Water storage tanks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
42 |  | Expansion tanks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
43 |  | Medical gas Oxygen system tanks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
44 |  | Medical gas Nitrogen system tanks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
45 |  | Medical gas Vacuum system tanks | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
46 |  | Medical waste interceptors | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
47 |  | Grease interceptors | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
48 |  | Oil interceptors | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
49 |  | Waste Interceptors | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.
50 |  | Medical gas devices | These are listed in the Fixture Schedule. A Take Off will be required to get the quantities.

## ELECTRICAL
No. | ELECTRICAL | Commercial & Healthcare Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | Skechers ITB Tyler Texas 0Mini | Skechers ITB Tyler Texas 40 | Skechers ITB Tyler Texas 401 | Skechers ITB Tyler Texas 401 mini
1 |  | What is the Name of the Electrical (MEP) Engineering Firm?
2 |  | What is the name of the Electrical Engineer?
3 |  | What is the full address of the Electrical Engineer?
4 |  | What Documents are provided specific to Electrical? | Could be: Plans, As-Built Drawings, Specifications, SOW, Special Instructions, Rules & Regulations, Equipment Lists, Fixture Schedules, MOP Forms
5 |  | Where are the Electrial specifications located? | Specification Manual or Plans
6 |  | What Electrical Building codes are listed on the drawings? | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
7 |  | Power Distribution and Generation Equipment | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
8 |  | Main electrical service panels | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
9 |  | Switchgear | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
10 |  | Transformers | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
11 |  | Automatic transfer switches | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
12 |  | Circuit breaker panels | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
13 |  | Busway systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
14 |  | Motor control centers (MCCs) | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
15 |  | Emergency generators | These may be listed with the Electrical Equipment on the drawings. But a reference in the speciations will be where the details will be.
16 |  | Backup power systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
17 |  | Uninterruptible power supplies (UPS) | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
18 |  | Standby power systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
19 |  | Automatic load transfer equipment | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
20 |  | Redundant power systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
21 |  | Critical care power distribution panels | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
22 |  | Life safety electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
23 |  | Lighting Systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
24 |  | LED fixtures | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
25 |  | Fluorescent lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
26 |  | Recessed lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
27 |  | Surface-mounted fixtures | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
28 |  | Emergency lighting systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
29 |  | Exit sign lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
30 |  | Architectural lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
31 |  | Exterior area lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
32 |  | Dimmable lighting systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
33 |  | Occupancy sensor lighting controls | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
34 |  | Surgical suite lighting systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
35 |  | Exam room lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
36 |  | Color-corrected medical lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
37 |  | Adjustable intensity lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
38 |  | Sterile area lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
39 |  | Operating room overhead lights | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
40 |  | Procedure room lighting | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
41 |  | Electrical Devices and Outlets | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
42 |  | Receptacles (various types) | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
43 |  | Light switches | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
44 |  | Dimmer switches | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
45 |  | GFCI and AFCI outlets | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
46 |  | Data and communication outlets | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
47 |  | Floor boxes | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
48 |  | Ceiling-mounted electrical boxes | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
49 |  | Wiring devices | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
50 |  | Medical gas outlet electrical connections | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
51 |  | Patient room electrical headwalls | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
52 |  | Medical equipment power outlets | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
53 |  | Specialized medical device receptacles | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
54 |  | Control and Monitoring Systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
55 |  | Building management systems (BMS) | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
56 |  | Programmable logic controllers (PLCs) | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
57 |  | Electrical monitoring systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
58 |  | Energy management systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
59 |  | Lighting control systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
60 |  | Building automation systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
61 |  | Central monitoring stations | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
62 |  | Patient monitoring system electrical infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
63 |  | Medical equipment control systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
64 |  | Environmental monitoring systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
65 |  | Nurse station electrical controls | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
66 |  | Safety and Protection Systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
67 |  | Surge protection devices | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
68 |  | Grounding systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
69 |  | Arc fault circuit interrupters | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
70 |  | Ground fault circuit interrupters | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
71 |  | Electrical safety disconnect switches | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
72 |  | Medical-grade electrical isolation systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
73 |  | Emergency power off (EPO) systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
74 |  | Electrical systems for sterile environments | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
75 |  | Communication and Technology Infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
76 |  | Fire alarm control panels | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
77 |  | Security system equipment | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
78 |  | Access control systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
79 |  | Telecommunications equipment | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
80 |  | Data center electrical infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
81 |  | Audio-visual system equipment | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
82 |  | Nurse call systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
83 |  | Paging systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
84 |  | Wireless communication infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
85 |  | Telemedicine equipment electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
86 |  | Specialty and Treatment Equipment Power | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
87 |  | Electric vehicle charging stations | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
88 |  | Elevator electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
89 |  | HVAC electrical controls | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
90 |  | X-ray equipment electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
91 |  | MRI electrical infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
92 |  | CT scan power requirements | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
93 |  | Radiation therapy equipment power | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
94 |  | Laboratory equipment electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
95 |  | Surgical equipment power systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
96 |  | Specialized Environment Systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
97 |  | Isolated power systems for critical care areas | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
98 |  | Operating room electrical zones | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
99 |  | Isolation room electrical systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
100 |  | Clean room electrical infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
101 |  | Negative/positive pressure room electrical controls | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
102 |  | Medical gas alarm electrical interfaces | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
103 |  | Energy Management | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
104 |  | Energy monitoring systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
105 |  | Sustainable electrical infrastructure | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
106 |  | Power quality monitoring systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.
107 |  | Electrical load management systems | These may be listed in the Electrical Drawings. A Take Off will be required to get the quantities.

## FIRE SUPPRESSION
No. | FIRE SUPPRESSION | Commercial & Healthcare Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | Skechers ITB Tyler Texas 0Mini | Skechers ITB Tyler Texas 40 | Skechers ITB Tyler Texas 401 | Skechers ITB Tyler Texas 401 mini
1 |  | What is the Name of the Fire Suppression (MEP) Engineering Firm?
2 |  | What is the name of the Fire Suppression Engineer?
3 |  | What is the full address of the Fire Suppression Engineer?
4 |  | What Documents are provided specific to Fire Suppression? | Could be: Plans, As-Built Drawings, Specifications, SOW, Special Instructions, Rules & Regulations, Equipment Lists, Device Schedules
5 |  | Where are the Fire Suppression specifications located? | Specification Manual or Plans
6 |  | What Fire Supppression Building codes are listed on the drawings? | Typically they are listed as NFPA codes.
7 |  | What Type of Fire Suppression System is the basis of design? | There are 4 different types.
8 |  | 1 | Wet Pipe Systems: Most common type, with water constantly in the pipes, ready for immediate discharge
9 |  | 2 | Dry Pipe Systems: Used in cold environments where pipes might freeze; air pressure holds water back until activated
10 |  | 3 | Deluge Systems: Open nozzles that release water simultaneously over entire area, typically used in high-risk zones
11 |  | 4 | Pre-Action Systems: Combine characteristics of wet and dry systems, requiring two-stage activation
12 |  | Fire Pumps: | Fire Pumps: Provide additional water pressure for large buildings or areas with inadequate municipal water supply
14 |  | Fire Alarm Panels | Fire Alarm and Detection Equipment
15 |  | Duct Smoke Detectors: | Duct Smoke Detectors: Specifically designed to detect smoke in HVAC ductwork
16 |  | Voice Evacuation Systems: | Voice Evacuation Systems: Provide clear, specific instructions during emergency evacuation
17 |  | Area of Refuge Communication: | Area of Refuge Communication: Allow communication for individuals unable to immediately evacuate
18 |  | Clean Agent Systems: | Clean Agent Systems: Use gases or chemicals that don't damage sensitive equipment (ideal for server rooms, medical equipment)
19 |  | CO2 Systems: | CO2 Systems: Quickly suppress fires by removing oxygen, used in enclosed spaces with critical equipment
20 |  | Foam Suppression: | Foam Suppression: Effective for liquid fuel fires, creates a blanket to prevent re-ignition
21 |  | Kitchen Hood Systems: | Kitchen Hood Systems: Automatically suppress grease fires in commercial cooking areas
22 |  | Medical Gas Area Protection: | Medical Gas Area Protection: Special systems to prevent fire spread near oxygen and other medical gas systems
23 |  | Surgical Suite Systems: | Surgical Suite Systems: Extremely sensitive detection and suppression to protect critical medical environments
24 |  | Fire Dampers: | Fire Dampers: Prevent fire spread through HVAC ductwork
25 |  | Smoke Dampers: | Smoke Dampers: Control smoke movement during fire events
26 |  | Pressurization Systems: | Pressurization Systems: Maintain safe escape routes by controlling air pressure during fire

## FLOORING
No. | Flooring | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | SOME COMMON TERMS AND ABBREVIATIONS
1 |  | what is the warranty language | see first if there is flooring warranty language and then overall warranty language; Identify any applicable warranties in the specifications, summarize the warranty requirments, and provide the location within the plan set. Ensure warranty duration requirements are captured if available. | Polished Concrete | Sealed Concrete | Densified Concrete | Epoxy Flooring
|  | Is the project a new building or new first generation interior space, otherwise known as "new construction"? |  | Concrete Polishing, Burnished Concrete, Polish, Bomanite, Questmark, Diamond Polish, Diamond Polished Concrete, Stained Concrete, Dyed Concrete, Honed Concrete, | Acrylic, Sealer, Floor Sealer, Sealed, ArmorSeal | Penetrating Sealer, Densifier, Ashford Formula, Hardener, Dustproofing, Dustproofer, Diamond Hard, Hardened Concrete | Resinous Flooring, Epoxy Flake, Polyurethane, Urethane Cement, Cementitious Urethane, Polycrete, Poly-Crete, Dur-A-Flex, Sikafloor, Resuflor, Floor Coating, Epoxy Coating, Novolac
2 |  | Is this new construction? | new construction is taxed on materials only | PC, PC-01, PC-1, CON-1, CONC-1, CONC, PC1, PC01, PCONC, | SC, SC1, SC-1, SC-01, SEAL, SCONC | SC, SC1, SC-01, CONC | EPX, EPX-1, EPX-01, EPX1, EPX01, RES, RES-1, RES-01, RES1, RES01, EPOXY, EP-01, EP-1, EX, EX1
|  | Is the project a new building or new first generation interior space, otherwise known as "new construction"? | new construction is taxed on materials only
3 |  | Is the concrete new?
4 |  | According to the structural drawings, will a new concrete slab be poured for this project?
Will the existing slab be demolished and replaced?
Do the drawings contain a demolition ("demo") page that includes the demo of existing flooring? This may be located as its own plan set or within the architectual drawings.
5 |  | Does the slab have existing flooring such as wood, tile or carpet that will be removed?
6 |  | Is the slab on grade? | slab on grade will likely have joints to fill
7 |  | Are there multiple floors?
Are there levels (floors, stories) does the project consist of?
Provide the relevant pages for floor finishes
Provide the Finish Plan(s) and Finish Schedule (aka, Material Schedule, Room Finish Schedule)
Provide the designation used for Polished Concrete, Sealed Concrete, and Epoxy Flooring (PC-1, EPX-2, etc. etc.) AND the number of times the designation is used in the plans.
|  | Are there references to x in the Finish Notes? (loop) | x = Polished Concrete, Overlay, Sealed Concrete, Densified Concrete, Epoxy Floors, Resinous Floors, and Terrazzo.
7 |  | Find the relevant pages for x floor finish finishes
Is epoxy or resinous integral cove base required? If so, provide the height (if available) and any detail pages.
12 |  | Find the relevant pages for tile, wood or carpet | this isn't needed but is a proxy to see if there is anything other than tile, wood or carpet
13 |  | Are there rooms will have x installed?
18 |  | Are there rooms will received flooring other than wood, tile, or carpet?
19 |  | Does the specification call for x or is x listed in the Table of Contents? If so, provide the page locations, section reference, and section title.
20 |  | If Polished Concrete is present, is there a designated aggregate exposure level, sheen level, or color?
21 |  | If Sealed Concrete is present, do the plans designate acrylic vs. densifier, topical vs. penetrating, or a specific material to use? If so, please state those requirements.
22 |  | If Epoxy or Resinous Flooring is present, provide any designated material type, manufacturer, and/or description.
23 |  | Are there Addendums does this project have?
24 |  | Do the plans require any Phasing? If so, what are the requirements?
25
26
27
28

## 00-Procurement and Contracting
No. | 00-Procurement and Contracting | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 00-Procurement and Contracting contractor?
2. |  | What documents are provided specific to 00-Procurement and Contracting trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 00-Procurement and Contracting trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 00-Procurement and Contracting listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 00-Procurement and Contracting trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 00-Procurement and Contracting trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 00-Procurement and Contracting trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 00-Procurement and Contracting trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 00-Procurement and Contracting materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 00-Procurement and Contracting tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 00-Procurement and Contracting trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 00-Procurement and Contracting trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 00-Procurement and Contracting work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 00-Procurement and Contracting trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 00-Procurement and Contracting trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 00-Procurement and Contracting work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 00-Procurement and Contracting? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 00-Procurement and Contracting materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 00-Procurement and Contracting trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 00-Procurement and Contracting trade? | Include punch list or closeout documentation requirements.

## 01-General Requirements
No. | 01-General Requirements | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | PCM COMMENTS 1/29/25 | PCM COMMENT ABOUT THESE QUESTIONS:
1. |  | What is the name and full address of the 01-General Requirements contractor? |  | DIV 01 will apply to all Trades | 1 | These questions are intended to be "common" questions that would be used for the purposes of establishing preferences for a Sub's GO/NO-GO bid decision when the ITB is first received. The questions need to be written for the AI Agent to read and understand the bid documents and return an answer that helps the sub make a GO/NO-GO decision.
2. |  | What documents are provided specific to 01-General Requirements trades? | Could be: Plans, As-Built Drawings, Specifications. | Not critical to a GO/NO-GO Decision
3. |  | Are there any 01-General Requirements trade-specific certifications or licenses required? | Examples: State licenses, trade certifications. | This can be critical to a GO/NO-GO Decision
4. |  | Where are the specifications and standards for 01-General Requirements listed in the project documentation? | Specification Manual, Design Standards. | Not critical to a GO/NO-GO Decision | 2 | GC's will expect the Subs to read and understand the documents before asking any of these questions in and RFI.
5. |  | Are there any special site conditions affecting the 01-General Requirements trade? | Examples: Access limitations, safety constraints. | This can be critical to a GO/NO-GO Decision | 3 | If the HW AI Agents can read and understand the bid documents and answer these questions for the Sub's...it could be really helpful to them.
6. |  | What is the timeline for completing 01-General Requirements trade work? | Define key milestones and deadlines. | Not critical to a GO/NO-GO Decision | 4 | Some GC's and Sub's could see the AI Agent doing this work for them as a "negative". Keep in mind...one way for estimators to become familiar with the project contract documents is to read and understand them. If the Sub estimators become "dependent on AI Agents to answer all their questions without reviewing "ALL" of the documents...it could put them at risk of missing something critical to their scope of work or contract obligations.
7. |  | Are there subcontractor qualifications specific to the 01-General Requirements trade? | Describe qualifications or experience required. | This can be critical to a GO/NO-GO Decision
8. |  | Which materials are required for 01-General Requirements trade tasks? | List standard or project-specific materials. | Not critical to a GO/NO-GO Decision
9. |  | Are there preferred suppliers for 01-General Requirements materials or equipment? | Include details for any required supplier partnerships. | This can be critical to a GO/NO-GO Decision
10. |  | Are there pre-installation meetings required for 01-General Requirements tasks? | Outline requirements for pre-task coordination meetings. | This can be critical to a GO/NO-GO Decision |  |  | GO/NO GO Recommendation Questions | comments | Lots of these answers will be in 01-General Requirements
11. |  | How will quality control for the 01-General Requirements trade be managed? | Quality control checks or inspection standards. | This can be critical to a GO/NO-GO Decision |  |  | size | Actual project size (not scope size)
12. |  | Are there safety standards unique to the 01-General Requirements trade? | Focus on OSHA standards or project-specific requirements. | This can be critical to a GO/NO-GO Decision |  |  | location | (city state)
13. |  | Are there environmental concerns or regulations for 01-General Requirements work? | Consider waste disposal or compliance with environmental laws. | This can be critical to a GO/NO-GO Decision |  |  | project type | if project type is unknown from the design docs then we will manually check what project type it is
14. |  | What are the warranty requirements listed in the 01-General Requirements for trade materials or work? | Define warranty periods and conditions. | This can be critical to a GO/NO-GO Decision |  |  | Labor (prevailing wage project or not) | if not in the ITB (typically written in section 01-General Requirements) |  | will need to train AI that prevailing wage also means union
15. |  | Are mock-ups required for 01-General Requirements trade installations? | Specify any visual or functional mock-up requirements. | This can be critical to a GO/NO-GO Decision |  |  | Bond Requirements (Performance and Payment Bond Y/N) | not in ITB but will be in bid documents (typically written in section 01-General Requirements)
16. |  | What is the procedure for inspection of completed 01-General Requirements work? | Outline inspection protocols and responsible parties. | This can be critical to a GO/NO-GO Decision |  |  | Preferred GC
17. |  | Are there coordination requirements with other trades for 01-General Requirements? | Detail any trade dependencies or sequencing. | This can be critical to a GO/NO-GO Decision |  |  | Preferred Owner
18. |  | What are the storage requirements for 01-General Requirements materials on-site? | Highlight temperature, humidity, or other storage needs. | This can be critical to a GO/NO-GO Decision |  |  | New Construction or Remodal
19. |  | How will changes to 01-General Requirements trade specifications be handled? | Include processes for approvals or amendments. | Not critical to a GO/NO-GO Decision
20 |  | What are the post-completion requirements for the 01-General Requirements trade? | Include punch list or closeout documentation requirements. | This can be critical to a GO/NO-GO Decision

## 02-Existing Conditions
No. | 02-Existing Conditions | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | PCM COMMENTS 1/29/25
1. |  | What is the name and full address of the 02-Existing Conditions contractor? |  | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
2. |  | What documents are provided specific to 02-Existing Conditions work trades? | Could be: Plans, As-Built Drawings, Specifications. | This can be critical to a GO/NO-GO Decision
3. |  | Are there any 02-Existing Conditions trade-specific certifications or licenses required? | Examples: State licenses, trade certifications. | This can be critical to a GO/NO-GO Decision
4. |  | Where are the specifications and standards for 02-Existing Conditions listed in the project documentation? | Specification Manual, Design Standards. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
5. |  | Are there any special site conditions affecting the 02-Existing Conditions work? trade? | Examples: Access limitations, safety constraints. | This can be critical to a GO/NO-GO Decision
6. |  | What is the timeline for completing 02-Existing Conditions trade work? | Define key milestones and deadlines. | This can be critical to a GO/NO-GO Decision
7. |  | Are there subcontractor qualifications specific to the 02-Existing Conditions trade? | Describe qualifications or experience required. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
8. |  | Which materials are required for 02-Existing Conditions trade tasks? | List standard or project-specific materials. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
9. |  | Are there preferred suppliers for 02-Existing Conditions materials or equipment? | Include details for any required supplier partnerships. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
10. |  | Are there pre-installation meetings required for 02-Existing Conditions tasks? | Outline requirements for pre-task coordination meetings. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
11. |  | How will quality control for the 02-Existing Conditions work trade be managed? | Quality control checks or inspection standards. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
12. |  | Are there safety standards unique to the 02-Existing Conditions work trade? | Focus on OSHA standards or project-specific requirements. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
13. |  | Are there environmental concerns or regulations for 02-Existing Conditions work? | Consider waste disposal or compliance with environmental laws. | This can be critical to a GO/NO-GO Decision
14. |  | Is there a warranty required for 02-Existing Conditions trade materials or work? | Define warranty periods and conditions. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
15. |  | Are mock-ups required for 02-Existing Conditions trade installations? | Specify any visual or functional mock-up requirements. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
16. |  | What is the procedure for inspection of completed 02-Existing Conditions work? | Outline inspection protocols and responsible parties. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
17. |  | Are there coordination requirements with other trades for 02-Existing Conditions? | Detail any trade dependencies or sequencing. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
18. |  | What are the storage requirements for 02-Existing Conditions materials on-site? | Highlight temperature, humidity, or other storage needs. | This is not a realistic question - There is not an 02 Existing Conditions Contractor. This section generally applies to all trades that are part of the "existing Conditions work"
19. |  | How will changes to 02-Existing Conditions work trade specifications be handled? | Include processes for approvals or amendments. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision
20. |  | What are the post-completion requirements for the 02-Existing Conditions work trade? | Include punch list or closeout documentation requirements. | IMPORTANT but not CRITICAL to a GO/NO-GO Decision

## 03-Concrete
No. | 03-Concrete | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments | PCM COMMENTS 1/29/25 | PCM COMMENT ABOUT THESE QUESTIONS:
1. |  | What is the name and full address of the 03-Concrete contractor? |  | This is not a realistic question - The project is bidding now | 1 | These questions are intended to be "common" questions that would be used for the purposes of establishing preferences for a Sub's GO/NO-GO bid decision when the ITB is first received. The questions need to be written for the AI Agent to read and understand the bid documents and return an answer that helps the sub make a GO/NO-GO decision.
2. |  | What documents are provided specific to 03-Concrete trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 03-Concrete trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 03-Concrete listed in the project documentation? | Specification Manual, Design Standards. |  | 2 | GC's will expect the Subs to read and understand the documents before asking any of these questions in an RFI.
5. |  | Are there any special site conditions affecting the 03-Concrete trade? | Examples: Access limitations, safety constraints. |  | 3 | If the HW AI Agents can read and understand the bid documents and answer these questions for the Sub's...it could be really helpful to them.
6. |  | What is the timeline for completing 03-Concrete trade work? | Define key milestones and deadlines. |  | 4 | Some GC's and Sub's could see the AI Agent doing this work for them as a "negative". Keep in mind...one way for estimators to become familiar with the project contract documents is to read and understand them. If the Sub estimators become "dependent on AI Agents to answer all their questions without reviewing "ALL" of the documents...it could put them at risk of missing something critical to their scope of work or contract obligations.
7. |  | Are there subcontractor qualifications specific to the 03-Concrete trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 03-Concrete trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 03-Concrete materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 03-Concrete tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 03-Concrete trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 03-Concrete trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 03-Concrete work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 03-Concrete trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 03-Concrete trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 03-Concrete work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 03-Concrete? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 03-Concrete materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 03-Concrete trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 03-Concrete trade? | Include punch list or closeout documentation requirements.

## 04-Masonry
No. | 04-Masonry | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 04-Masonry contractor?
2. |  | What documents are provided specific to 04-Masonry trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 04-Masonry trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 04-Masonry listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 04-Masonry trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 04-Masonry trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 04-Masonry trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 04-Masonry trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 04-Masonry materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 04-Masonry tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 04-Masonry trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 04-Masonry trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 04-Masonry work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 04-Masonry trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 04-Masonry trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 04-Masonry work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 04-Masonry? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 04-Masonry materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 04-Masonry trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 04-Masonry trade? | Include punch list or closeout documentation requirements.

## 05-Metals
No. | 05-Metals | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 05-Metals contractor?
2. |  | What documents are provided specific to 05-Metals trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 05-Metals trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 05-Metals listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 05-Metals trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 05-Metals trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 05-Metals trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 05-Metals trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 05-Metals materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 05-Metals tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 05-Metals trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 05-Metals trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 05-Metals work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 05-Metals trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 05-Metals trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 05-Metals work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 05-Metals? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 05-Metals materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 05-Metals trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 05-Metals trade? | Include punch list or closeout documentation requirements.

## 06-Wood, Plastics, and Composit
No. | 06-Wood, Plastics, and Composit | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 06-Wood, Plastics, and Composit contractor?
2. |  | What documents are provided specific to 06-Wood, Plastics, and Composit trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 06-Wood, Plastics, and Composit trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 06-Wood, Plastics, and Composit listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 06-Wood, Plastics, and Composit trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 06-Wood, Plastics, and Composit trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 06-Wood, Plastics, and Composit trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 06-Wood, Plastics, and Composit trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 06-Wood, Plastics, and Composit materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 06-Wood, Plastics, and Composit tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 06-Wood, Plastics, and Composit trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 06-Wood, Plastics, and Composit trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 06-Wood, Plastics, and Composit work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 06-Wood, Plastics, and Composit trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 06-Wood, Plastics, and Composit trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 06-Wood, Plastics, and Composit work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 06-Wood, Plastics, and Composit? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 06-Wood, Plastics, and Composit materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 06-Wood, Plastics, and Composit trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 06-Wood, Plastics, and Composit trade? | Include punch list or closeout documentation requirements.

## 07-Thermal and Moisture Protect
No. | 07-Thermal and Moisture Protect | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 07-Thermal and Moisture Protect contractor?
2. |  | What documents are provided specific to 07-Thermal and Moisture Protect trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 07-Thermal and Moisture Protect trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 07-Thermal and Moisture Protect listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 07-Thermal and Moisture Protect trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 07-Thermal and Moisture Protect trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 07-Thermal and Moisture Protect trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 07-Thermal and Moisture Protect trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 07-Thermal and Moisture Protect materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 07-Thermal and Moisture Protect tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 07-Thermal and Moisture Protect trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 07-Thermal and Moisture Protect trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 07-Thermal and Moisture Protect work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 07-Thermal and Moisture Protect trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 07-Thermal and Moisture Protect trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 07-Thermal and Moisture Protect work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 07-Thermal and Moisture Protect? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 07-Thermal and Moisture Protect materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 07-Thermal and Moisture Protect trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 07-Thermal and Moisture Protect trade? | Include punch list or closeout documentation requirements.

## 08-Openings
No. | 08-Openings | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 08-Openings contractor?
2. |  | What documents are provided specific to 08-Openings trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 08-Openings trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 08-Openings listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 08-Openings trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 08-Openings trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 08-Openings trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 08-Openings trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 08-Openings materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 08-Openings tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 08-Openings trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 08-Openings trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 08-Openings work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 08-Openings trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 08-Openings trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 08-Openings work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 08-Openings? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 08-Openings materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 08-Openings trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 08-Openings trade? | Include punch list or closeout documentation requirements.

## 09-Finishes
No. | 09-Finishes | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 09-Finishes contractor?
2. |  | What documents are provided specific to 09-Finishes trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 09-Finishes trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 09-Finishes listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 09-Finishes trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 09-Finishes trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 09-Finishes trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 09-Finishes trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 09-Finishes materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 09-Finishes tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 09-Finishes trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 09-Finishes trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 09-Finishes work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 09-Finishes trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 09-Finishes trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 09-Finishes work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 09-Finishes? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 09-Finishes materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 09-Finishes trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 09-Finishes trade? | Include punch list or closeout documentation requirements.

## 10-Specialties
No. | 10-Specialties | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 10-Specialties contractor?
2. |  | What documents are provided specific to 10-Specialties trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 10-Specialties trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 10-Specialties listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 10-Specialties trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 10-Specialties trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 10-Specialties trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 10-Specialties trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 10-Specialties materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 10-Specialties tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 10-Specialties trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 10-Specialties trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 10-Specialties work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 10-Specialties trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 10-Specialties trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 10-Specialties work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 10-Specialties? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 10-Specialties materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 10-Specialties trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 10-Specialties trade? | Include punch list or closeout documentation requirements.

## 11-Equipment
No. | 11-Equipment | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 11-Equipment contractor?
2. |  | What documents are provided specific to 11-Equipment trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 11-Equipment trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 11-Equipment listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 11-Equipment trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 11-Equipment trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 11-Equipment trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 11-Equipment trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 11-Equipment materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 11-Equipment tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 11-Equipment trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 11-Equipment trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 11-Equipment work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 11-Equipment trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 11-Equipment trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 11-Equipment work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 11-Equipment? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 11-Equipment materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 11-Equipment trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 11-Equipment trade? | Include punch list or closeout documentation requirements.

## 12-Furnishings
No. | 12-Furnishings | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 12-Furnishings contractor?
2. |  | What documents are provided specific to 12-Furnishings trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 12-Furnishings trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 12-Furnishings listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 12-Furnishings trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 12-Furnishings trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 12-Furnishings trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 12-Furnishings trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 12-Furnishings materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 12-Furnishings tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 12-Furnishings trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 12-Furnishings trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 12-Furnishings work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 12-Furnishings trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 12-Furnishings trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 12-Furnishings work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 12-Furnishings? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 12-Furnishings materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 12-Furnishings trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 12-Furnishings trade? | Include punch list or closeout documentation requirements.

## 13 — Special Construction
No. | 13 — Special Construction | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 13 — Special Construction contractor?
2. |  | What documents are provided specific to 13 — Special Construction trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 13 — Special Construction trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 13 — Special Construction listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 13 — Special Construction trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 13 — Special Construction trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 13 — Special Construction trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 13 — Special Construction trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 13 — Special Construction materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 13 — Special Construction tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 13 — Special Construction trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 13 — Special Construction trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 13 — Special Construction work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 13 — Special Construction trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 13 — Special Construction trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 13 — Special Construction work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 13 — Special Construction? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 13 — Special Construction materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 13 — Special Construction trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 13 — Special Construction trade? | Include punch list or closeout documentation requirements.

## 14 — Conveying Equipment
No. | 14 — Conveying Equipment | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 14 — Conveying Equipment contractor?
2. |  | What documents are provided specific to 14 — Conveying Equipment trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 14 — Conveying Equipment trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 14 — Conveying Equipment listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 14 — Conveying Equipment trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 14 — Conveying Equipment trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 14 — Conveying Equipment trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 14 — Conveying Equipment trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 14 — Conveying Equipment materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 14 — Conveying Equipment tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 14 — Conveying Equipment trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 14 — Conveying Equipment trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 14 — Conveying Equipment work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 14 — Conveying Equipment trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 14 — Conveying Equipment trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 14 — Conveying Equipment work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 14 — Conveying Equipment? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 14 — Conveying Equipment materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 14 — Conveying Equipment trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 14 — Conveying Equipment trade? | Include punch list or closeout documentation requirements.

## 21 — Fire Suppression
No. | 21 — Fire Suppression | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 21 — Fire Suppression contractor?
2. |  | What documents are provided specific to 21 — Fire Suppression trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 21 — Fire Suppression trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 21 — Fire Suppression listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 21 — Fire Suppression trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 21 — Fire Suppression trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 21 — Fire Suppression trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 21 — Fire Suppression trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 21 — Fire Suppression materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 21 — Fire Suppression tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 21 — Fire Suppression trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 21 — Fire Suppression trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 21 — Fire Suppression work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 21 — Fire Suppression trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 21 — Fire Suppression trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 21 — Fire Suppression work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 21 — Fire Suppression? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 21 — Fire Suppression materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 21 — Fire Suppression trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 21 — Fire Suppression trade? | Include punch list or closeout documentation requirements.

## 22 — Plumbing
No. | 22 — Plumbing | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 22 — Plumbing contractor?
2. |  | What documents are provided specific to 22 — Plumbing trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 22 — Plumbing trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 22 — Plumbing listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 22 — Plumbing trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 22 — Plumbing trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 22 — Plumbing trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 22 — Plumbing trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 22 — Plumbing materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 22 — Plumbing tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 22 — Plumbing trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 22 — Plumbing trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 22 — Plumbing work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 22 — Plumbing trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 22 — Plumbing trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 22 — Plumbing work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 22 — Plumbing? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 22 — Plumbing materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 22 — Plumbing trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 22 — Plumbing trade? | Include punch list or closeout documentation requirements.

## 23 — Heating, Ventilating, and
No. | 23 — Heating, Ventilating, and | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 23 — Heating, Ventilating, and contractor?
2. |  | What documents are provided specific to 23 — Heating, Ventilating, and trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 23 — Heating, Ventilating, and trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 23 — Heating, Ventilating, and listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 23 — Heating, Ventilating, and trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 23 — Heating, Ventilating, and trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 23 — Heating, Ventilating, and trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 23 — Heating, Ventilating, and trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 23 — Heating, Ventilating, and materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 23 — Heating, Ventilating, and tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 23 — Heating, Ventilating, and trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 23 — Heating, Ventilating, and trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 23 — Heating, Ventilating, and work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 23 — Heating, Ventilating, and trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 23 — Heating, Ventilating, and trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 23 — Heating, Ventilating, and work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 23 — Heating, Ventilating, and? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 23 — Heating, Ventilating, and materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 23 — Heating, Ventilating, and trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 23 — Heating, Ventilating, and trade? | Include punch list or closeout documentation requirements.

## 25 — Integrated Automation
No. | 25 — Integrated Automation | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 25 — Integrated Automation contractor?
2. |  | What documents are provided specific to 25 — Integrated Automation trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 25 — Integrated Automation trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 25 — Integrated Automation listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 25 — Integrated Automation trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 25 — Integrated Automation trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 25 — Integrated Automation trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 25 — Integrated Automation trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 25 — Integrated Automation materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 25 — Integrated Automation tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 25 — Integrated Automation trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 25 — Integrated Automation trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 25 — Integrated Automation work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 25 — Integrated Automation trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 25 — Integrated Automation trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 25 — Integrated Automation work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 25 — Integrated Automation? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 25 — Integrated Automation materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 25 — Integrated Automation trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 25 — Integrated Automation trade? | Include punch list or closeout documentation requirements.

## 26 — Electrical
No. | 26 — Electrical | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 26 — Electrical contractor?
2. |  | What documents are provided specific to 26 — Electrical trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 26 — Electrical trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 26 — Electrical listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 26 — Electrical trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 26 — Electrical trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 26 — Electrical trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 26 — Electrical trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 26 — Electrical materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 26 — Electrical tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 26 — Electrical trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 26 — Electrical trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 26 — Electrical work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 26 — Electrical trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 26 — Electrical trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 26 — Electrical work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 26 — Electrical? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 26 — Electrical materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 26 — Electrical trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 26 — Electrical trade? | Include punch list or closeout documentation requirements.

## 27 — Communications
No. | 27 — Communications | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 27 — Communications contractor?
2. |  | What documents are provided specific to 27 — Communications trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 27 — Communications trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 27 — Communications listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 27 — Communications trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 27 — Communications trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 27 — Communications trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 27 — Communications trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 27 — Communications materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 27 — Communications tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 27 — Communications trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 27 — Communications trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 27 — Communications work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 27 — Communications trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 27 — Communications trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 27 — Communications work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 27 — Communications? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 27 — Communications materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 27 — Communications trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 27 — Communications trade? | Include punch list or closeout documentation requirements.

## 28 — Electronic Safety and Secu
No. | 28 — Electronic Safety and Secu | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 28 — Electronic Safety and Secu contractor?
2. |  | What documents are provided specific to 28 — Electronic Safety and Secu trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 28 — Electronic Safety and Secu trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 28 — Electronic Safety and Secu listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 28 — Electronic Safety and Secu trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 28 — Electronic Safety and Secu trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 28 — Electronic Safety and Secu trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 28 — Electronic Safety and Secu trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 28 — Electronic Safety and Secu materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 28 — Electronic Safety and Secu tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 28 — Electronic Safety and Secu trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 28 — Electronic Safety and Secu trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 28 — Electronic Safety and Secu work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 28 — Electronic Safety and Secu trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 28 — Electronic Safety and Secu trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 28 — Electronic Safety and Secu work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 28 — Electronic Safety and Secu? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 28 — Electronic Safety and Secu materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 28 — Electronic Safety and Secu trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 28 — Electronic Safety and Secu trade? | Include punch list or closeout documentation requirements.

## 31 — Earthwork
No. | 31 — Earthwork | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 31 — Earthwork contractor?
2. |  | What documents are provided specific to 31 — Earthwork trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 31 — Earthwork trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 31 — Earthwork listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 31 — Earthwork trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 31 — Earthwork trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 31 — Earthwork trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 31 — Earthwork trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 31 — Earthwork materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 31 — Earthwork tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 31 — Earthwork trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 31 — Earthwork trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 31 — Earthwork work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 31 — Earthwork trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 31 — Earthwork trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 31 — Earthwork work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 31 — Earthwork? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 31 — Earthwork materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 31 — Earthwork trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 31 — Earthwork trade? | Include punch list or closeout documentation requirements.

## 32 — Exterior Improvements
No. | 32 — Exterior Improvements | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 32 — Exterior Improvements contractor?
2. |  | What documents are provided specific to 32 — Exterior Improvements trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 32 — Exterior Improvements trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 32 — Exterior Improvements listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 32 — Exterior Improvements trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 32 — Exterior Improvements trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 32 — Exterior Improvements trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 32 — Exterior Improvements trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 32 — Exterior Improvements materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 32 — Exterior Improvements tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 32 — Exterior Improvements trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 32 — Exterior Improvements trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 32 — Exterior Improvements work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 32 — Exterior Improvements trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 32 — Exterior Improvements trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 32 — Exterior Improvements work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 32 — Exterior Improvements? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 32 — Exterior Improvements materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 32 — Exterior Improvements trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 32 — Exterior Improvements trade? | Include punch list or closeout documentation requirements.

## 33 — Utilities
No. | 33 — Utilities | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1. |  | What is the name and full address of the 33 — Utilities contractor?
2. |  | What documents are provided specific to 33 — Utilities trades? | Could be: Plans, As-Built Drawings, Specifications.
3. |  | Are there any 33 — Utilities trade-specific certifications or licenses required? | Examples: State licenses, trade certifications.
4. |  | Where are the specifications and standards for 33 — Utilities listed in the project documentation? | Specification Manual, Design Standards.
5. |  | Are there any special site conditions affecting the 33 — Utilities trade? | Examples: Access limitations, safety constraints.
6. |  | What is the timeline for completing 33 — Utilities trade work? | Define key milestones and deadlines.
7. |  | Are there subcontractor qualifications specific to the 33 — Utilities trade? | Describe qualifications or experience required.
8. |  | Which materials are required for 33 — Utilities trade tasks? | List standard or project-specific materials.
9. |  | Are there preferred suppliers for 33 — Utilities materials or equipment? | Include details for any required supplier partnerships.
10. |  | Are there pre-installation meetings required for 33 — Utilities tasks? | Outline requirements for pre-task coordination meetings.
11. |  | How will quality control for the 33 — Utilities trade be managed? | Quality control checks or inspection standards.
12. |  | Are there safety standards unique to the 33 — Utilities trade? | Focus on OSHA standards or project-specific requirements.
13. |  | Are there environmental concerns or regulations for 33 — Utilities work? | Consider waste disposal or compliance with environmental laws.
14. |  | Is there a warranty required for 33 — Utilities trade materials or work? | Define warranty periods and conditions.
15. |  | Are mock-ups required for 33 — Utilities trade installations? | Specify any visual or functional mock-up requirements.
16. |  | What is the procedure for inspection of completed 33 — Utilities work? | Outline inspection protocols and responsible parties.
17. |  | Are there coordination requirements with other trades for 33 — Utilities? | Detail any trade dependencies or sequencing.
18. |  | What are the storage requirements for 33 — Utilities materials on-site? | Highlight temperature, humidity, or other storage needs.
19. |  | How will changes to 33 — Utilities trade specifications be handled? | Include processes for approvals or amendments.
20. |  | What are the post-completion requirements for the 33 — Utilities trade? | Include punch list or closeout documentation requirements.

## 05 -- STEEL
No. | 05 — STEEL | Commercial Construction ITB or RFP - Supplier or Subcontractor Questions | Comments
1 |  | Is this project delivered by a _General Contractor_ or a _Construction Manager_? Return only one of [General Contractor, Construction Manager]. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
2 |  | Does this project include a bid form? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
3 |  | Does the project require a bid bond? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
4 |  | Who provides joists and deck? Return only one of [Owner, GC, CM]. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
5 |  | Does the project require a payment and performance bond? Yes or No only. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
6 |  | What is the bid-delivery method? Return only one of [Design-Bid-Build, CMAR, Design-Build, IPD]. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
7 |  | s the bid opening public or private? Return only one of [Public, Private]. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
8 |  | Is this project fabricationnonly? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata filename: [filename.pdf] human_readable: [title] page_num: [##] sheet_number: [sheet] section: [section] ```
9 |  | Does the project require an erection number? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
10 |  | Does the job require a union erector? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...``
11 |  | Is the project turnkey? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
12 |  | Does the project include architecturally exposed structural steel (AESS)? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
13 |  | Which paint system is required? Return one of [Alkyd, Epoxy, GalvZinc, Other]. Provide one short sentence explaining where you found that info. ```metadata ...```
14 |  | Is surface blasting required? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
15 |  | What primer type and colour are required? Return only the primer name/code. Provide one short sentence explaining where you found that info. ```metadata ...```
16 |  | Is stairnandnrail design required? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
17 |  | Are stairs & rails / miscnsteel issued as a separate package? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
18 |  | Do steel connections need to be designed by the fabricator? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
19 |  | Is designnassist required on this project? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
20 |  | Is an engineer’s stamp required? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
21 |  | What is the construction type? Return one of . Provide one short sentence explaining where you found that info. ```metadata ...```
22 |  | Does the scope include rolled steel material? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
23 |  | Is a sample contract included in the specifications? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
24 |  | Are addenda issued for this project? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
25 |  | Is alternate pricing requested? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
26 |  | Is any material supplied by the customer? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
27 |  | Is there a proposed schedule in the bid documents? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
28 |  | Is the project pursuing LEED certification? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
29 |  | Is the project subject to BuynAmerican/domesticnonly requirements? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
30 |  | Are special steel grades required? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
31 |  | Does the job require an AISCncertified fabricator? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
32 |  | Does the job require an AISCncertified erector? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
33 |  | Does the job require AISC paint certification? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
34 |  | Is a prevailingnwage requirement in effect? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
35 |  | Does DavisnBacon wage apply? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
36 |  | Is there a WBE/MBE participation requirement? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
37 |  | Are testing & inspection requirements specified? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
38 |  | Is the project sales AND tax exempt? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
39 |  | What is the salesntax rate for the project? Return only the number (percent). Provide one short sentence explaining where you found that info. ```metadata ...```
40 |  | What is the warranty period for the project? Return only the number of months. Provide one short sentence explaining where you found that info. ```metadata ...```
41 |  | Are liquidated damages or penalties specified? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
42 |  | What is the liquidated and damages amount? Return only the number. Provide one short sentence explaining where you found that info. ```metadata ...```
43 |  | What are the payment terms? Return one of [Net 30, Net 45, Net 60, Other]. Provide one short sentence explaining where you found that info. ```metadata ...```
44 |  | What are the retainage terms? Return one of [5 %, 10 %, Other]. Provide one short sentence explaining where you found that info. ```metadata ...```
45 |  | s certified payroll required? Answer Yes or No only. Provide one short sentence explaining where you found that info. ```metadata ...```
46 |  | Is the project covered by OCIP or CCIP? Return one of [OCIP, CCIP]. Provide one short sentence explaining where you found that info. ```metadata ...```
47 |  | How long must the bid remain valid? Return only the number of days. Provide one short sentence explaining where you found that info. ```metadata ...```